## April
Days	Week	Tasks	Status at the end of the week before Mondays (starting, in progress, consolidated, finished)	Comments in case of errors
From 03/04 to 07/04	1	Install: / a. Operating System: Linux / b. JoularJX: https://www.noureddine.org/research/joular/joularjx2. / c. python 3 / d. Maven >= 3.6.3 / e. R and Rstudio / f. IDE, for instance Eclipse.
		Understand how JoularJX estimates power consumption (power models, granularity of measurements). To do that, read the paper “Biblio/2022_Noureddine_PowerJoular_and_JoularJX.pdf” and prepare a brief summary, ex. 01_JoularJX_summary in the Summary folder.
		Execute preliminary experiments with JoularJX. To do that: / a. see the Java projects in the “Code/Prem_Experiment” folder. / b. adapt the bash and python scripts to run at least 30 executions per Java code or project. / c. adapt the python script to analyse collected data, in particular we would like to analyse the type of data distribution (performing the saphiro test), and to generate plots of data distributions. If you prefer you can use R for it.
From 10/04 to 14/04	2	First experiment

From 17/04 to 21/04	3	Run an experiment on the cMath project. Run the test cases in this project attaching JoularJx. Run at least 30 executions of Java Project. And provide information of saphiro test.

From 24/04 to 28/04	4	Second experiment

## May
Days	Week	Tasks	Status at the end of the week before Mondays (starting, in progress, consolidated, finished)	Comments in case of errors
From 02/05 to 05/05	1	Read papers about code refactoring and energy efficiency.

From 08/05 to 12/05	2	Read papers about genetic improvement		Focus on the paper related to Gin tool: 2019_Gin__Genetic_Improvement_2019_Research_Made_Easy.pdf

From 15/05 to 19/05	3

From 22/05 to 26/05	4	Introduction of genetic improvement (GI) toolbox (i.e. Gin). / https://github.com/gintool/gin

From 29/05 to 02/06	5	Analyse how to integrate code refactoring to Gin, prepare a proof of concept

## June
Days	Week	Tasks	Status at the end of the week before Mondays (starting, in progress, consolidated, finished)	Comments in case of errors
From 05/06 to 09/06	1

From 12/06 to 16/06	2

From 19/06 to 23/06	3

From 26/06 to 30/06	4

## July
Days	Week	Tasks	Status at the end of the week before Mondays (starting, in progress, consolidated, finished)	Comments in case of errors
From 03/07 to 07/07	1

From 10/07 to 14/07	2

From 17/07 to 21/07	3

From 24/07 to 28/07	4

## August
Days	Week	Tasks	Status at the end of the week before Mondays (starting, in progress, consolidated, finished)	Comments in case of errors
From 31/07 to 04/08	1	Internship report

From 07/08 to 11/08	2

From 14/08 to 18/08	3

From 21/08 to 25/08	4	Internship presentation and rehearsal

From 28/08 to 31/08	4	Internship presentation and rehearsal